5U AI — 90-DAY EXECUTION ROADMAP

31 July – 29 October 2026 · Executes the S1+S2-first, S4-pilot, S3-gated sequencing from 5U-AI-MECE-Strategy.docx. Ties to the live 5U-AI-Scenario-Model.xlsx — gate results update the scenario each quarter.

# 1. Objective and the one guardrail

Start the two cheapest, highest-leverage levers immediately (partner channel, pricing), run a small paid test of the road-freight pool, and hold the self-serve product decision until it has evidence.

Guardrail that overrides everything else: never book more forward-deployed customers than FDE capacity can serve (1 FDE ≈ 10 accounts). If pipeline outruns hiring, throttle sales before quality slips — this was the single biggest failure mode in the stress test.

# 2. Roadmap at a glance

| Workstream | Month 1 (Wk 1–4) | Month 2 (Wk 5–8) | Month 3 (Wk 9–13) |
| --- | --- | --- | --- |
| Pricing (S2) | Publish rate card + deployment fee | Monitor win rate; adjust if needed | Lock in as standard or revise |
| Contract fixes | Legal redraft: liability, SLA, CPI cap | Send to active renewals | Standard in all new paper |
| Partner channel (S1) | CargoWise certification application; Timocom outreach | Certification live; Timocom listing + co-marketing | First partner-sourced leads worked |
| Road pilot (S4) | Identify 5–10 Timocom-connected prospects | Run 2–3 paid discovery pilots (FDE-delivered, by exception) | Gate decision: fund roadmap or park |
| Self-serve (S3) | No build — track only | Landing page + waitlist (signal only) | Not gated yet — review at day 180 |
| Reference logos | Shortlist 3 candidates, offer terms | Close 1–2 at discount | Case study drafted |
| Events | Book Ghent + Milan + Berlin | Attend T&L Ghent (Sep 22–23) | Attend FIATA Milan (Oct 6–9), BVL Berlin (Oct 21–22) |
| Capacity/hiring | Open FDE #3 + GTM hire reqs | Interview and offer | FDE #3 onboarded before pipeline lands |

# 3. Week-by-week plan

| Week | Milestone | Owner | Exit criteria |
| --- | --- | --- | --- |
| 1 | Legal engaged on contract fixes (liability cap → 1x annual fees, 99.5% SLA, CPI+3% cap) | CEO + outside counsel | Redline drafted |
| 1 | CargoWise partner-certification application submitted | CTO | Application acknowledged |
| 1 | Timocom partnership conversation opened | CTO / GTM hire | First call booked |
| 2 | Rate card finalized (Launch→Enterprise, €30k–€108k) and published on site | CEO | Live URL |
| 2 | Per-additional-Worker deployment fee (~€4.5k) added to standard contract | CEO + legal | New template in use |
| 2 | 3 reference-logo candidates shortlisted; discount terms drafted (≤20%, max 3 accounts) | CEO | Offers sent |
| 3–4 | Comparison pages drafted (vs Nexcade, Copilot Studio/n8n, DIY) | GTM hire | 2 pages live |
| 3–4 | FDE #3 and Founding GTM hire reqs posted; pipeline of candidates started | CEO/CTO | ≥5 candidates each in process |
| 5–6 | CargoWise certification finalized; co-marketing asset agreed | CTO | Certified badge usable |
| 5–6 | Timocom listing live; road-pool prospect list built (5–10 names) | GTM hire | Listing live + list ready |
| 6 | Ghent (T&L) and Milan (FIATA) logistics booked: registrations, meeting lists pre-scheduled | CEO | Bookings confirmed |
| 7–8 | 2–3 paid road-freight discovery pilots kicked off (priced, not free). FDE-delivered by exception — the output is the Road Charter Worker spec, not a book of FDE-served road accounts | FDE lead | Pilots signed; Worker requirements logged |
| 8 | Attend Transport & Logistics Ghent (22–23 Sep) — beachhead pipeline meetings | CEO/GTM hire | ≥15 qualified meetings |
| 9 | FDE #3 onboarded and ramping | CTO | Started |
| 10 | Attend FIATA World Congress, Milan (6–9 Oct) — reputation + peer-proof intros | CEO | ≥5 partner/reference conversations |
| 11 | First partner-sourced leads (CargoWise/Timocom) worked by GTM hire | GTM hire | ≥3 leads in pipeline |
| 12 | Attend BVL Supply Chain CX, Berlin (21–22 Oct) — EU-AI-Act / decision-layer thought leadership | CEO | Talk or panel delivered |
| 13 | Day-90 gate review against Scenario Model; decide scale/kill per workstream | CEO + CTO | Gate decisions logged |

# 4. Budget (90 days)

Modest against the ~€2.95m pre-seed cash on hand; this is a test-and-learn budget, not a growth-spend budget.

| Line item | Cost | Note |
| --- | --- | --- |
| Legal — contract redraft | €15,000 | Liability, SLA, CPI clause, cross-training opt-out |
| CargoWise certification + partner program fees | €8,000 | One-time + first-year fee |
| Timocom listing / partnership setup | €4,000 | Estimate — confirm with Timocom commercial team |
| Comparison pages + content (design/copy) | €8,000 | Freelance or agency |
| Reference-logo discounts (revenue foregone, not cash) | ~€36,000 | 3 accounts × €60k ACV × 20% — opportunity cost, tracked separately from cash spend |
| Events — Ghent (attend; entry free, travel only) | €1,500 |  |
| Events — FIATA Milan (€580 under-35 rate + travel) | €3,000 | Centenary edition. Book by 15 Sep. A stand would add ~€22k, decide separately |
| Events — BVL Berlin (€900 start-up ticket + travel) | €2,000 |  |
| Recruiting — FDE #3 + Founding GTM hire | €25,000 | Agency/sourcing fees; salaries already in Scenario Model opex |
| Cash total (excl. discount foregone) | ~€66,500 | ~2% of pre-seed cash — leaves runway intact |

# 5. Day-90 gate review — scale, adjust, or kill

| Workstream | Metric | Scale if… | Kill/hold if… |
| --- | --- | --- | --- |
| Partner channel (S1) | Certified + partner-sourced leads | ≥3 qualified leads by Wk 13 | <3 — revisit co-marketing terms, don't abandon (asset already built) |
| Pricing (S2) | Win rate vs pre-publish baseline | Stable ±5pts or better | Drops >5pts — test a 10% lower anchor before reverting |
| Road pilot (S4) | Signed paid pilots | ≥2 signed by Wk 13 — fund the Worker; steady-state road delivery moves to the marketplace | 0–1 — park until customs Worker ships |
| Self-serve (S3) | Waitlist signups (signal only) | N/A — not gated this cycle | Review full build decision at day 180 per MECE strategy |
| Capacity | FDE utilisation | <85%, FDE #3 ramped | ≥85% or hiring behind plan → throttle new logos immediately |

# 6. Ownership (RACI, condensed for a 7–person team)

| Area | Owner (Accountable) | Support |
| --- | --- | --- |
| Pricing, reference logos, event reputation | CEO (Yagiz) | GTM hire |
| CargoWise/Timocom technical certification | CTO (Fehmi) | Engineering |
| Partner outreach, road-pilot prospecting, events logistics | Founding GTM hire | CEO |
| Road pilot delivery, FDE capacity planning | FDE lead | CTO |
| Contract redraft | CEO | Outside counsel |

# 7. Risks to this plan

- Hiring slips. FDE #3 and the GTM hire are on the critical path for weeks 3–9; a slow search delays the partner-lead follow-up and the road pilots simultaneously. Start sourcing week 1, not after the legal/pricing work clears.

- Event spend concentrated in one month. All three events land in Sep–Oct; book registrations/flights in weeks 1–6 to avoid last-minute price spikes; FIATA's under-35 rate closes 15 Sep.

- Partner certification timeline is not fully in 5U AI's control. CargoWise's own review process could push past week 6 — submit week 1 to buy maximum buffer.

- Self-serve underinvestment risk. Deliberately not building this quarter is correct per the model, but don't let “not gated yet” become “forgotten” — the day-180 decision needs the waitlist data collected now.